## Cover Page
Big Data Course
Capstone Project
Work Breakdown Structure
For students
ⓒ2023 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung Innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today
Project Team Name |  | Team 6
Project Topic |  | SentimentGuard: Real-time Sentiment Classification of Live Chat Comments for Early Detection of Harmful Comment Spikes
Task |  |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4
[8 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20
[8 empty] | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04
1. Project planning and management | [6 empty] | In-progress
| Team setup and topic framing |  | 2026-09-15 | 2026-09-16 | Ký | docs/topic_decision.md | Done | bar: 2026-09-15 to 2026-09-16
| Action Plan preparation |  | 2026-09-16 | 2026-09-17 | Ký, Dẳm | deliverables/Action_Plan.docx | Done | bar: 2026-09-16 to 2026-09-17
| Data selection and source/licence verification |  | 2026-09-16 | 2026-09-18 | Hạnh | data/raw/SOURCE.md | Done | bar: 2026-09-16 to 2026-09-18
| Work Breakdown Structure (WBS) preparation |  | 2026-09-18 | 2026-09-18 | Ký | deliverables/WBS.xlsx | In-progress | bar: 2026-09-18
| Preliminary presentation (Day 5) |  | 2026-09-18 | 2026-09-19 | All members | Proposal slides | Delayed | bar: 2026-09-18 to 2026-09-19
| WBS revision for review checkpoints |  | 2026-09-23 | 2026-09-24 | Ký | Updated WBS.xlsx (checks Day 9, 14, 19) | Delayed | bar: 2026-09-23 to 2026-09-24
2. Data preparation | [6 empty] | Delayed
| Data quality assessment (duplicates, rating distribution) |  | 2026-09-20 | 2026-09-21 | Hạnh | Quality report table | Delayed | bar: 2026-09-20 to 2026-09-21
| Shared text-cleaning module with unit tests |  | 2026-09-20 | 2026-09-21 | Dẳm | src/common/text_cleaning.py | Delayed | bar: 2026-09-20 to 2026-09-21
| Rating-to-sentiment mapping, dedup, fixed split |  | 2026-09-21 | 2026-09-22 | Hạnh | data/processed/ + eval_labels.parquet | Delayed | bar: 2026-09-21 to 2026-09-22
3. Data ingestion pipeline (Kafka) | [6 empty] | Delayed
| Kafka setup, topics and configuration |  | 2026-09-22 | 2026-09-23 | Bằng | kafka/ scripts + README | Delayed | bar: 2026-09-22 to 2026-09-23
| Replay producer (rate, burst, late records) |  | 2026-09-23 | 2026-09-24 | Bằng | src/producer/replay_producer.py | Delayed | bar: 2026-09-23 to 2026-09-24
| Ingestion throughput measurement |  | 2026-09-24 | 2026-09-24 | Bằng | outputs/tables/ingestion_*.csv | Delayed | bar: 2026-09-24
4. Data transformation (Spark Structured Streaming) | [6 empty] | Delayed
| Streaming job: explicit schema, cleaning, DLQ |  | 2026-09-24 | 2026-09-25 | Dẳm | src/streaming/stream_job.py | Delayed | bar: 2026-09-24 to 2026-09-25
| Event-time windows and watermark aggregation |  | 2026-09-25 | 2026-09-26 | Dẳm | Parquet aggregates | Delayed | bar: 2026-09-25 to 2026-09-26
| Fault-tolerance test (restart mid-stream) |  | 2026-09-26 | 2026-09-27 | Dẳm | Test results table | Delayed | bar: 2026-09-26 to 2026-09-27
5. Model training and evaluation | [6 empty] | Delayed
| Spark ML pipeline; TF-IDF fitted on train only |  | 2026-09-25 | 2026-09-26 | Hạnh | src/training/train_model.py | Delayed | bar: 2026-09-25 to 2026-09-26
| Training and tuning with class weights |  | 2026-09-26 | 2026-09-27 | Hạnh | outputs/models/ | Delayed | bar: 2026-09-26 to 2026-09-27
| Final test evaluation: macro-F1, per-class metrics |  | 2026-09-27 | 2026-09-28 | Hạnh | outputs/tables/metrics.csv | Delayed | bar: 2026-09-27 to 2026-09-28
6. Query, visualization and dashboard | [6 empty] | Delayed
| Spark SQL queries and aggregation tables |  | 2026-09-28 | 2026-09-29 | Nguyên | src/eda/ | Delayed | bar: 2026-09-28 to 2026-09-29
| Figures and insight notes |  | 2026-09-29 | 2026-09-30 | Nguyên | outputs/figures/, insights.md | Delayed | bar: 2026-09-29 to 2026-09-30
| Streamlit dashboard and alert threshold |  | 2026-09-30 | 2026-10-01 | Nguyên | src/app/app.py | Delayed | bar: 2026-09-30 to 2026-10-01
7. Prototype demonstration and delivery | [6 empty] | Delayed
| Prototype showing presentation (Day 11) |  | 2026-09-25 | 2026-09-25 | All members | Prototype slides | Delayed | bar: 2026-09-25
| Usage scenario and operating guide |  | 2026-10-01 | 2026-10-02 | Dẳm, Ký | docs/scenario.md | Delayed | bar: 2026-10-01 to 2026-10-02
| Final report (Day 18) |  | 2026-10-01 | 2026-10-02 | All members | deliverables/Final_Report.docx | Delayed | bar: 2026-10-01 to 2026-10-02
| Final presentation and live demo (Day 20) |  | 2026-10-03 | 2026-10-04 | All members | Final slides | Delayed | bar: 2026-10-03 to 2026-10-04